## Milestone 3
Milestone 2 Tasks | SubTask | Teammate | Description |  |  | m1-oct 13 |  | m2- oct 20 | m3- oct 27 | m4-nov 3 | m5-nov 10 | DEADLINE:: Nov 12th
Control Documents |  | Matt | standard docs | [7 empty] | Done
| Change log | Matt | Everyone is responsible for recording their own edits and reporting them at each meeting. If you make any edit to a document increment the document name by .1 and make a personal note |  |  | in progress |  | in progress | in progress | in progress | Done | Done
| RRM | Matt | RRM |  |  | in progress |  | Should have been done | Done | Done | Done | Done
Client Documents |  | Matt |  |  |  | Needs to be written |  | Needs to be written | Needs to be written | Needs to be written | Done | Needs to be written
| Opening Statement | Matt |  |  |  | Needs to be written |  | Needs to be written | Needs to be written | Needs to be written | Done | Needs to be written
| Executive Statement | Matt |  |  |  | Needs to be written |  | Needs to be written | Needs to be written | Needs to be written | Done | Needs to be written
| Implications For Cloient | Matt |  |  |  | Needs to be written |  | Needs to be written | Needs to be written | Needs to be written | Done | Needs to be written
| Items For Approval | Matt |  |  |  | Needs to be written |  | Needs to be written | Needs to be written | Needs to be written | Done | Needs to be written
Tracking Gantt Chart |  | Brevan/Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Update Project 2013 Baseline | Brevan/Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Create Tracking Gantt Chart | Brevan/Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Create Variance Report | Brevan/Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
Baseline Project Plan |  | Doug |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Introduction | Doug |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Systems Description | Doug |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Feasibility Assessment | Doug |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
Requirements Documentation |  | Doug |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Stakeholder | Doug |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Requirements | Doug |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Category | Doug |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Priority | Doug |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Acceptance Criteria | Doug |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
Risk Register |  | Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Risk ID | Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Risk Statement | Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Impact | Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Score | Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| Response | Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
Security Policies |  | Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| P1 | Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| P2 | Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| P3 | Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
Appendices |  | Brevan |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| AA:Email | Brevan |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| AB:Meeting Minutes | Brevan |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| AC: Analysis Diagrams | Brevan |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| AD: Project Management | Brevan |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| AE:Econ Benefit Analysis | Brevan |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
| AF:Tracking Gantt Chart | Brevan/Matt |  |  |  | Research Needed |  | Research Needed | Research Needed | Research Needed | Research Needed | Research Needed
Peer Evaluations |  | All
Start Date | Due Date | duration | days left in project | to m2 | to m3 | to m4 | to m5
2016-10-09 | 2016-11-12 | 34 | 4 | -19 | -12 | -5 | 2

## RRM
name | role | Responsibilities | Detail - All tasks fall under a responsibility but individual tasks can be done by anyone, it's just that the responsible person is who takes responsibility
Matt | M3 manager
|  | Project Management | oversee progress of project on macro level
|  | Version Control | track and manage changes to final project
|  | Running Document management | Pageation, grammar, and structure of the Running Document
Brevan | Lead Developer
|  | Database Development | Development of the Access Program and it's implementation
|  | Technical Document's Management | Graphs, Diagrams, and Project 2016 file
Appendicies
Douglas | Administrative Manager
|  | M3 Document management | Full research and development of documents for the Milestone binder
Client Documents

## Meeting Minutes
Date | agenda | progress | todo | notes
2016-10-13 | Finalize Roles and responsibilities
Determine work breakdown
Identify problem areas
Work on fixing M2 document for Saturday
2016-10-20
2016-10-27
2016-11-03
2016-11-10
2016-11-12

## Change log
date | time | document name | document version | changes made | document name | version
2016-09-10 | 13:00 | example doc | v1.0 | change1
change2
change3
change4

## Guidelines
Maintain your change log and submit it at each meeting, Matt will use this to build the master change log and track changes so they can be merged
Versions::: Matt has the master version of everything which will be submitted. You will receive a copy of the master. If possible separate distinct areas into individual documents, if not possible then highlight your changes in yellow. Make sure that you thoroughly document your change log so I can find all of your changes.
Try to keep as much of your conversations in a single thread as possible, the standard naming convention is M3-m1.0 this stands for Milestone 1 Meeting 1.0. The Meeting version relates to the distinct meetings listed under meeting minutes. If you need to send something to the group and need a seperate thread increment the meeting version by .1 (ie. m1.1)